## Sheet1
No | Sprint | Task | Owner | Estimated Time (Hr) | Actual Time (Hr)
1 | 1 (Nov 6) | Audio Recording - backend | Mook | 5
2 | 1 (Nov 6) | Audio Recording - frontend | Mook | 5 |  | Please refer to project specification and wireframe for more detail
3 | 1 (Nov 6) | Song List page (Simple version) | Mook | 2
4 | 1 (Nov 6) | Song List model | Mook | 1
5 | 1 (Nov 6) | Study SoundCloud API | Lely | 5
6 | 1 (Nov 6) | Audio Upload | Lely | 5
7 | 1 (Nov 6) | Audio Player | Lely | 5
8 | 1 (Nov 6) | Front-end structure (HTML/CSS) | Lely | 2
9 | 1 (Nov 6) | User/Group model | Ome | 2
10 | 1 (Nov 6) | User can request to join the band | Ome | 2
11 | 1 (Nov 6) | Authentication | Rush | 2
12 | 1 (Nov 6) | Home page : Display user/group information | Rush | 2
13 | 1 (Nov 6) | User registration | Rush | 2
14 | 2 (Nov 20) | Calendar Display | TBC
15 | 2 (Nov 20) | Adding event (Practice Session) | TBC
16 | 2 (Nov 20) | Event link to song list | TBC
17 | 2 (Nov 20) | Song list - image uploader | TBC
18 | 2 (Nov 20) | Band information page | TBC